FY 2026 Annual Schedule for KS-507

FY 2026 KS BoS CoC Competition Timeline

	Date
	Event
	Description

	June 1, 2026
	HUD FY 2026 CoC NOFO Released & Public Notice
	HUD issues the FY 2026 CoC Program Notice of Funding Opportunity. NOFO posted to CoC Membership Listserv and KSHC website.

	June 1, 2026
	Public Notification of HUD Release of CoC NOFO by CoC Lead; Website & Social Media
	KSHC, as Collaborative Applicant, posts public notice of the NOFO release on the KS BoS CoC website and social media channels.

	June 4 -June 11
	P&C Committee Review of FY 2026 NOFO Policy Updates
	Performance & Compliance Committee reviews: Competition Timeline, updated Renewal and New Project Scoring Matrices, updated NOFO Policies, and nomination of Rank & Review Panel members.

	June 12
	Steering Committee Review & Approve CoC NOFO Policies and Scoring Matrix
	Steering Committee vote on: Competition Timeline, updated Scoring Matrices, NOFO Policies, Appeals Procedure, Rank & Review Panel members.

	June 15
	Letter of Intent (LOI) Opens for New & Renewal Projects
	Renewal, Voluntary Reallocations, Transitions, Consolidations, New Bonus Projects, New Transitional Housing Projects, Expansion Projects, or New SSO Projects. 

KSHC will provide TA throughout LOI period to confirm thresholds and alignment with HUD’s FY26 priorities. 

	June 15
	Renewal Project Performance Score Cards Distributed to Agencies
	HMIS-Generated Performance Scorecards distributed to all renewal agencies.

	June 18-19
	HMIS Renewal Scorecard Office Hours 
	Optional for renewal agencies with questions about their HMIS-Generated Performance Scorecards. Renewals can schedule time with the HMIS Team for final review during this window. 

	June 24
	Mandatory CoC NOFO Training 


	New Applicants: 10:00 AM – 11:30 AM
Renewal Applicants: 2:00 PM – 3:30 PM

ALL renewal and new project applicants must attend to be eligible to submit a local application. Training covers: FY 2026 program changes, new priority project types (TH and SSO), updated scoring criteria, HUD project-type minimum thresholds, and eSNAPS requirements.

	July 1

	Letter of Intent Deadline at 5:00pm
 
	Submission required through the KSHC online application portal. KSHC staff review all LOIs for HUD eligibility thresholds and local participation requirements. New and Renewal projects passing threshold will be invited to submit a local application. Projects failing to meet threshold will be notified in writing and will not advance.

	July 6
	Local Application Opens
	Agencies that pass threshold review are invited to submit a local application. 

	July 17 5:00pm
	Deadline for Local Application

	Final deadline for local applications via the KSHC online application portal. Once submitted, the local application is locked; no changes are permitted until after Rank & Review is complete.


	TBD
	Rank & Review Training
	Rank & Review Panel members will receive training on the FY26 local competition process, scoring tools, conflict of interest requirements, confidentiality expectations, reallocation review, and procedures for documenting scoring decisions.

	July 20-23
	Rank & Review Panel Reviews Local Applications
	KSHC prepares applications, scorecards, HMIS data, and the Flagged for Involuntary Reallocation list for panel review. The Rank & Review Panel prepares the Preliminary Priority Listing and submits it to the Steering Committee.

	July 24
	Steering Committee Reviews, Approves Preliminary Listing
	The Steering Committee reviews the Rank & Review Panel’s preliminary scoring results, project ranking, tier placement, and any recommendations for rejection, reduction, reallocation, or conditional approval prior to applicant notification.

	July 24
	Applicants Notified in Writing — Preliminary Tier Listing Published
	Applicants notified via email of rank, score, tier, and appeal rights. Preliminary Tier Listing published on the KS BoS CoC website.

ALL project applicants notified IN WRITING (outside of eSNAPS) of accepted, rejected, or reduced status — including ranked position and, where applicable, the reason(s) for rejection or reduction.

	July 29 5:00pm
	Letter of Appeal due 
	Letter of appeal due to KSHC via electronic mail by 5:00pm. Submitting agency must follow the posted appeals process and procedure outlined in the CoC NOFO Policies. Agencies have 3 days from Preliminary Tier Listing to appeal.

	July 30
	Appeals Subcommittee meets to review appeal(s). 
	Written decision rendered to appellant and submitted to Steering Committee.

	August 3
	Agency eSNAPS Application Open.
	Agencies revise project applications in eSNAPS as needed based on funding reductions, technical clarification, and R&R Panel notes.


	August 14 5:00pm
	Agency eSNAPS Application deadline.
	Notify KSHC of completed application.

	August 17-20
	KSHC Review Agency eSNAPS Application
	KSHC staff review submitted project applications in eSNAPS for completeness, consistency with the approved local application, funding amounts, project type eligibility, required attachments, and technical corrections prior to final CoC submission.

	August 21
	Steering Committee Vote to Approve CoC Consolidated Application
	Steering Committee votes to approve the final CoC Consolidated Application package, including the Collaborative Application, Priority Listing, ranked project applications, and any final funding or ranking recommendations, prior to submission to HUD.

	Aug 24
	KSHC submits the Collaborative Application, Priority Listing and all Project Applications to HUD.
	KSHC submits the CoC Collaborative Application, CoC Priority Listing, and all approved project applications in eSNAPS before the HUD deadline. KSHC will export and retain the submission summary as proof of timely submission.

	August 26, 2026
	Final submission of CoC Consolidated Due
	Hard deadline established by HUD in the FY 2026 NOFO. No submissions accepted after 8:00 PM Eastern Time. KS BoS CoC targets submission no later than August 24 to allow a 48-hour buffer.

	December 1, 2026
	Expected HUD Award Announcement (per Congressional mandate P.L. 119-75)
	Per Congressional mandate (P.L. 119-75), HUD is directed to announce FY 2026 CoC Program awards on or about this date. Actual announcement date is subject to HUD discretion.





	
	
	



